## Slide 1: Production log
Fermata

## Slide 2: Client approval
Each week you will need to show your client (teacher) the completed work for approval. All work must all be agreed upon by the team as a whole. This is to highlight individual contributions and to have accountability for all team members throughout production.

## Slide 3: Week 1
Team Member | Contribution | Incomplete
Wing Him Choi | Dragon Rigging & Skinning | 
Tiarna Kilmister | Dragon Texturing (4 variants) | 
Glittika (Nancy) Gerdmanee | Concepting powerup icons | Powerup icons
Richard (Doug) Tilden | ??? | 
Finn Perry | Added cheat console, re-did scripts for dragons, critters and powerups. | 
Were all deliverables completed for the week?
Unsure
If not, how will the team compensate for this moving forward?
Work over the weekend.

## Slide 4: Week 2
Team Member | Contribution | Incomplete
Wing Him Choi | Dragon animations: walk, shoot, idle, stunned | 
Tiarna Kilmister | Finished dragon textures, environment textures, UV unwrapping environment assets | 
Glittika (Nancy) Gerdmanee | Drawing out Power Up Icons | 
Richard (Doug) Tilden |  | 
Finn Perry | Game balancing, added dashing, finished core gameplay. | 
Were all deliverables completed for the week? Yes

## Slide 5: Week 3
Team Member | Contribution | Incomplete
Wing Him Choi | Bomb prop, Bunny Animations, Special Powerup prop, Pedestal prop | 
Tiarna Kilmister | Retouched dragon textures, added bunny texture, finished environment textures | 
Glittika (Nancy) Gerdmanee | Arena layout, UI concepting (Score/Health Display) | 
Finn Perry | Dragon animation tree/blending. Bunny colours and death effects. | 
Were all deliverables completed for the week?
If not, how will the team compensate for this moving forward?

## Slide 6: Week 4
Team Member | Contribution | Incomplete
Wing Him Choi |  | 
Tiarna Kilmister |  | 
Glittika (Nancy) Gerdmanee |  | 
Richard (Doug) Tilden |  | 
Finn Perry |  | 
Were all deliverables completed for the week?
If not, how will the team compensate for this moving forward?

## Slide 7: Week 5
Team Member | Contribution | Incomplete
Wing Him Choi |  | 
Tiarna Kilmister |  | 
Glittika (Nancy) Gerdmanee |  | 
Richard (Doug) Tilden |  | 
Finn Perry |  | 
Were all deliverables completed for the week?
If not, how will the team compensate for this moving forward?

## Slide 8: Week 6
Team Member | Contribution | Incomplete
Wing Him Choi |  | 
Tiarna Kilmister |  | 
Glittika (Nancy) Gerdmanee |  | 
Richard (Doug) Tilden |  | 
Finn Perry |  | 
Were all deliverables completed for the week?
If not, how will the team compensate for this moving forward?

## Slide 9: Milestone & feedback log

## Slide 10: Client approval
There must be a minimum of 3 sessions where you present the project to the client (teacher), and they provide items of feedback for you to respond to. These should line up with 3 important milestone dates.

## Slide 11: Milestone 1 – intended outcome
Milestone Date: 2nd November 2018
List the work that is intended to be delivered for this milestone:
Arena Greybox
Particle Effects
Power Up Icons
Complete Forest Arena
Refine dragon model
Rig, unwrap, & texture dragon model
Icon display for power ups
Bunny animations

## Slide 12: Milestone 1 – outcome review
Delivered | Not Delivered | Client Feedback
Planned response to feedback for next milestone:

## Slide 13: Milestone 2 – intended outcome
Milestone Date: 15th November 2018
List the work that is intended to be delivered for this milestone:
Refine UI
Gag Achievements
Dragon animations
Programming power ups

## Slide 14: Milestone 2 – outcome review
Delivered | Not Delivered | Client Feedback
Planned response to feedback for next milestone:

## Slide 15: Milestone 3 – intended outcome
Milestone Date: 30th November 2018
List the work that is intended to be delivered for this milestone:
Gameplay balanced
Polished textures
Polished animations
Refined game
BGM and sound effects

## Slide 16: Milestone 3 – outcome review
Delivered | Not Delivered | Client Feedback
Planned response to feedback for next milestone: