## Slide 1: Production log
Fermata

## Slide 2: Client approval
Each week you will need to show your client (teacher) the completed work for approval. All work must all be agreed upon by the team as a whole. This is to highlight individual contributions and to have accountability for all team members throughout production.

## Slide 3: Week 1
Team Member | Contribution | Incomplete
Wing Him Choi | Dragon Rigging & Skinning | 
Tiarna Kilmister | Dragon Texturing (4 variants) | 
Glittika (Nancy) Gerdmanee | Concepting powerup icons | Powerup icons
Richard (Doug) Tilden | ??? | 
Finn Perry | Added cheat console, re-did scripts for dragons, critters and powerups. | 
Were all deliverables completed for the week?
Unsure
If not, how will the team compensate for this moving forward?
Work over the weekend.

## Slide 4: Week 2
Team Member | Contribution | Incomplete
Wing Him Choi | Dragon animations: walk, shoot, idle, stunned | 
Tiarna Kilmister | Finished dragon textures, environment textures, UV unwrapping environment assets | 
Glittika (Nancy) Gerdmanee | Drawing out Power Up Icons | 
Richard (Doug) Tilden |  | 
Finn Perry | Game balancing, added dashing, finished core gameplay. | 
Were all deliverables completed for the week? Yes

## Slide 5: Week 3
Team Member | Contribution | Incomplete
Wing Him Choi | Bomb prop, Bunny Animations, Special Powerup prop, Pedestal prop | 
Tiarna Kilmister | Retouched dragon textures, added bunny texture, finished environment textures | 
Glittika (Nancy) Gerdmanee | Arena layout, UI concepting (Score/Health Display) | 
Finn Perry | Dragon animation tree/blending. Bunny colours and death effects. | 
Were all deliverables completed for the week? Yes

## Slide 6: Week 4
Team Member | Contribution | Incomplete
Wing Him Choi | Dragon victory animation, skinning adjustments, dizzy star model | 
Tiarna Kilmister | Modelled pedestals, textured pedestals, redid black and white bunny textures, worked on title | 
Glittika (Nancy) Gerdmanee | End Screen UI visuals, Images for Instructions/How To Play, UI Animation, Menu UI visuals | 
Finn Perry | Bug fixes, updated textures, fixed hitboxes, updated menu and end scene, added new powerup model. | 
Were all deliverables completed for the week? Yes

## Slide 7: Week 5
Team Member | Contribution | Incomplete
Wing Him Choi | Dragon Victory and Defeat animations, minor prop modelling, playtesting & footage recording | 
Tiarna Kilmister | Game countdown numbers, playtesting & footage recording | 
Glittika (Nancy) Gerdmanee | UI for controller/player indicator, start menu/tutorial UI, playtesting & footage recording | 
Finn Perry | Changed freeze to aoe, bug fixes, fixed menu to work with controller, playtesting & footage recording | 
Were all deliverables completed for the week? Yes

## Slide 8: Week 6
Team Member | Contribution | Incomplete
Wing Him Choi | Footage recording and video editing for the trailer | 
Tiarna Kilmister | Playtesting | 
Glittika (Nancy) Gerdmanee | UI Background, Font Search, BGM & SFX, Main Menu animations | 
Finn Perry | Optimization, fixed bugs, added red damage tint, added dynamic spawn positions. | 
Were all deliverables completed for the week? Yes

## Slide 9: Milestone & feedback log

## Slide 10: Client approval
There must be a minimum of 3 sessions where you present the project to the client (teacher), and they provide items of feedback for you to respond to. These should line up with 3 important milestone dates.

## Slide 11: Milestone 1 – intended outcome
Milestone Date: 2nd November 2018
List the work that is intended to be delivered for this milestone:
Arena Greybox
Particle Effects
Power Up Icons
Complete Forest Arena
Refine dragon model
Rig, unwrap, & texture dragon model
Icon display for power ups
Bunny animations

## Slide 12: Milestone 1 – outcome review
Delivered | Not Delivered | Client Feedback
Arena Greybox |  | 
Particle Effects |  | 
Power Up Icons |  | Make it more clear what the powerups are.
Complete Forest Arena |  | 
Dragon Model |  | Cute
Bunny animations |  | Bunnies too small, mistaken for other animals
Planned response to feedback for next milestone: Make bunnies bigger, make powerup icons bigger

## Slide 13: Milestone 2 – intended outcome
Milestone Date: 15th November 2018
List the work that is intended to be delivered for this milestone:
Refine UI
Dragon animations
Programming power ups

## Slide 14: Milestone 2 – outcome review
Delivered | Not Delivered | Client Feedback
Player Display UI, Stage Select UI, Powerup Icons | Menu UI, Custom Font(s) | Make it more clear what the powerups are, show which common powerup is going to be picked up
Dragon animations |  | More squash and stretch, some indicator for the dragon being hit
Programming power ups |  | Powerups that changed playstyle were nice, powerups that simply added slightly on regular attack were less interesting
Planned response to feedback for next milestone: Implement clearer UI, refine animations, adjustments to powerups (most notably freeze powerup).

## Slide 15: Milestone 3 – intended outcome
Milestone Date: 28th November 2018
List the work that is intended to be delivered for this milestone:
Gameplay balanced
Polished textures
Polished animations
Refined game
BGM and sound effects

## Slide 16: Milestone 3 – outcome review
Delivered | Not Delivered | Client Feedback
Gameplay balanced |  | Get more player feedback to balance better. Spawn rates seem unbalanced.
Refined game (UI, extras) |  | UI is clearer! Cleaner.
Art polish |  | Clean. Animations work well.
BGM and sound effects | Dragon Roar, Dash sound effect | Clean up attack sound
Planned response to feedback for the end: In class or at event, have more people play the game to provide feedback on balance, refine sounds, add sounds that are missing.