## Sheet1
Week ending | 30-Sep | 7-Oct | 14-Oct | 21-Oct | 28-Oct | 4-Nov | 11-Nov | 18-Nov | 25-Nov | 30-Nov
Design | Game Design Document |  | Draft UI Interface (Main Menu) |  | Arena Greybox | Particle Effects Power Up Icons Put together Forest Arena | Refine UI Interface | Gag Achievements | Place Dragon & Rabbit animations in game Any refinements | BGM Sound Effects Any refinements
Art | Art Bible | Concept Art | 1st pass model of Dragon & Rabbit 1st pass Environmental Assets (Forest) | Refine Rabbit model Rig, unwrap & texture Rabbit model Texture Environmental Assets | Refine Dragon model | Rig, unwrap & texture Dragon model Animate Rabbit movement |  | Animate Dragon movement & attack | Any refinements | Any refinements
Programming | Technical Document Draft Dragon Movement | Health Bars Standard Attack (Short range Fire) | Player Stun (when 0 health) Critter spawn & movements |  | Power Ups |  | Icon Display |  | Gag Achievements Any refinements | Any refinements
Week | Pre-Production |  |  |  | Production